## M&E plan
M&E Plan
Code | Description | Indicator | Indicator definition | Level of disaggregation | Means of verification | Frequency of data collection | Tool | Responsibility
highrachey objectives
Impact (Goal) | TBD
OUTCOME 1 | Equip migrant and deprived Next Gen in Shanghai with essential human skills and digital skills | 1.1 # of trained youth with gains in human mindsets | Numerator: number of trained Next Gen with improved human skills scores Denominator: total number of trained Next Gen | by school and gender | Pre- and post survey to trained Next Gen | One time | Survey | Feng Lin
|  | 1.2 # of trained Next Gen with improved goal setting and confidence | Numerator: number of trained Next Gen with improved goal setting and confidence scores Denominator: total number of trained Next Gen | by school and gender | Pre- and post survey to trained Next Gen | One time | Survey | Feng Lin
|  | 1.3 # of Next Gen youth with gains in STEM and digital mindsets | Youth with increased interest in STEM and digital technology | by school and gender | create a post-test using the digital assessment for a randonly selected number of students from two schools | One time in May | Create a post-test using digital assessment and add STEM quesitons | Cheng Mian and Zhou Ji
Output 1.1 | Modified human skills curriculum that tailored to fourth grade adolescents | 1.1.1 # of modified human skills curriculum developed |  | N.A | Hard copy of human skills curriculum | One time |  | Feng Lin
Output 1.2 | Teachers trained on delivering human skills curriculum | 1.2.1 # of TOT plans developed |  |  | TOT plan | One time |  | Feng Lin
|  | 1.2.2 # of teacher training sessions |  |  | Training record |  | Training record sheet
|  | 1.2.3 # of teachers trained |  | by school and gender | Training record |  | Training record sheet
Output 1.3 | Target Next Gen trained on human skills | 1.3.1 # of Next Gen trained on human skills |  | by school and gender | Enrollment list from teachers Baseline | One time | List from teachers Baseline | Han Yanfei
Output 1.4 | Digital clubs established | 1.4.1 # of digital clubs established |  | by school | Program documentation | One time |  | Zhou Ji
OUTCOME 2 | Next Gen youth improve attitudes towards gender equality | Number of youth with improved attitudes towards gender equality |  | by school and gender | Gender assessment as the baseline and post-test | Pre and post | Gender assessment and post-test
OUTCOME 2 | Generate solid evidence to inform future programming |  |  |  | SEL Assessment Evaluation
Output 2.1 | Gender-based digital assessment conducted | 2.1.1 # of gender-based digital assessment report developed |  | Students Parents | Hard copy of digital assessment report | One time |  | Cheng Mian
Output 2.2 | Research/evaluation study conducted | 2.2.1 # of research/evaluation studies conducted |  | N/A | Preliminary Findings for the interim Report Final Report | One time |  | Cheng Mian
Output 2.3 | Digital skills framework developed | 2.3.1 # of digital skills framework developed |  | N/A | Powerpoint slides from ADP |  |  | ADP
Output 2.4 | Learning for action plan developed | 2.4.1 # of learning for action plans |  | N/A | Hard copy of learning action plan | One time |  | Zhou Ji and Cheng Mian
OUTCOME 3 | Parents and teachers raise awareness on the value of digital learning
Output 3.1 | Parents trained about the value of digital learning and the various career pathways via training workshops | 3.1.1 # of parent training workshops organized (in-person and online) | For online videos, count one workshop per semester for the series of videos distributed to teachers for parents. For in-person workshop, count workshop per each school per semester | by school | Activity record | One time | Activity record sheet | Zhou Ji
|  | 3.1.2 # of parents trained | For online videos, parents who have watched at least five clips can be counted as trained For in-person workshop, parents who attend a workshop will be counted | by school and gender | Online: Teacher confirmation once a semester (teachers ask parents and get their response) In-person: Attendance record | One time | Online: Teacher confirmation In-person: Attendance sheet | Zhou Ji
Output 3.2 | Experience-sharing sessions host for parents, teachers and school officials | 3.2.1 # of experience-sharing sessions held | Stakeholder meetings held at each school at the end of the program to share program and program results to students, teachers, parents, local educational authorities and media | by school | Activity record | One time | Activity record sheet | Zhou Ji